GovProxy

AI Adoption Intelligence Platform

V1 Build Specification

May 2026 — Build-Ready

CONFIDENTIAL

Understand how your teams adopt AI tools, detect waste,

track improvement, and coach developers toward effective AI-assisted work.

Prepared by: Goran  |  WirelessMedia Group

# 1. V1 Scope

An AI adoption intelligence platform that an engineering manager can deploy, connect to their GitHub org and Copilot admin, and within an hour see a unified view of AI tool adoption — who's using what, what it costs, whether it's working, and where money is wasted.

## Six Capabilities:

- GitHub Copilot connector — pull per-user usage metrics via admin API

- Git repository analysis — detect AI adoption signals from commit history

- Expense/subscription tracking — import cost data for all tools including reimbursed accounts

- Unified dashboard — cross-source view with waste detection and adoption trends

- Time-series storage with aggregation — daily snapshots, weekly/monthly pre-computed aggregates

- AI-generated summaries — automated weekly and monthly narrative reports

# 2. Tech Stack

| Layer | Choice | Rationale |
| --- | --- | --- |
| Runtime | Node.js + TypeScript | Existing expertise, fast iteration |
| Web Framework | Fastify | Lightweight API server for dashboard |
| Storage | SQLite (better-sqlite3) | Zero-config. PostgreSQL in v1.5 |
| Dashboard | React + Tailwind | SPA served by Fastify |
| CLI | Commander.js | Setup, sync, import, diagnostics |
| Scheduling | node-cron | Daily syncs, aggregation jobs |
| Git Analysis | GitHub REST API | Clone-free commit analysis |
| AI Summaries | Configurable LLM | Ollama / Haiku / Sonnet |
| Config | YAML + JSON Schema | Declarative, git-friendly |
| Packaging | Docker + npm global | Docker for deploy, npm for dev |

# 3. Development Phases

| Phase | Weeks | Focus | Milestone |
| --- | --- | --- | --- |
| 1 | 1–3 | Git + Copilot + Claude Code + Windsurf + foundation | Data pipeline running, API serving data, waste detected |
| 2 | 4–5 | Dashboard + waste detection UI | Manager sees unified cross-source view in browser |
| 3 | 6–7 | Aggregation engine + AI summaries | Automated weekly/monthly reports generated |
| 4 | 9 | Expense import + subscription tracking | Cost data overlaid, duplicate seats detected |
| 5 | 9–10 | Trends + advanced analytics | Longitudinal charts, team comparison, quarterly reports |
| 6 | 11–14 | Dogfood at WMG | 4 weeks real-world validation with 6 teams |

# 4. Phase 1: Detailed Tasks (Weeks 1–3)

Phase 1 validates the entire data pipeline before investing in dashboard UI. After 3 weeks you have: working connectors pulling data daily, time-series snapshots stored, waste detection running, and a REST API ready for the dashboard.

### Task 1.1: Project Scaffold (Day 1)

- TypeScript project with Fastify, better-sqlite3, Commander.js, vitest

- CLAUDE.md in project root

- Config loader with YAML + JSON Schema validation

- Docker and docker-compose files

Accept: npm run dev starts server. GET /health returns ok. Config validates. Tests pass.

### Task 1.2: Database + Migrations (Day 1–2)

- SQLite adapter with connection management

- Numbered migration system (5 migration files covering all tables + indexes)

- CLI: govproxy db migrate and govproxy db status

Accept: Migrate creates all tables. Idempotent. Status shows state. CRUD tests pass.

### Task 1.3: Developer & Team Registry (Day 2–3)

- CLI commands: team add/list, dev add/list/link

- Developer external_ids JSON for mapping across tools

- Auto-discovery from GitHub org members API

- Config-based team definitions

Accept: Teams and devs created via CLI. External IDs stored correctly. Auto-discovery pulls GitHub org members.

### Task 1.4: GitHub Copilot Connector (Day 3–6)

- Copilot Metrics API client: per-user daily suggestions, acceptances, by IDE/language/model

- Team attribution via metrics/teams endpoint

- Seat management: detect assigned, active, inactive seats

- Transform Copilot response → tool_snapshots records

- CLI: govproxy sync copilot

- Handle pagination, rate limits, errors gracefully

Accept: Sync populates tool_snapshots. Counts match. Inactive seats detected. API errors don’t crash. Tests with fixtures.

### Task 1.5: Git Repository Analysis (Day 6–10)

- GitHub REST API client for commits, PRs, reviews (no cloning)

- Per-developer daily: commits, lines changed, PRs, time-to-merge

- Code churn calculator: same file re-changed within 48h window

- AI signature scorer: heuristic-based (0-100), conservative, labeled as estimated

- Commit burst detection: 3+ commits within 30 minutes

- CLI: govproxy sync git

Accept: git_snapshots populated correctly. Churn rate calculated. AI score >0 for obvious AI patterns, 0 for normal. Handles empty repos.

### Task 1.6: Expense & Subscription Import (Day 10–12)

- CSV importer with configurable column mapping

- CLI: govproxy expenses import / govproxy expenses show

- Match imported data to developers via email

- Duplicate subscription detection

- Default cost values from config

Accept: CSV creates subscription records. Flexible column mapping. Duplicates detected. Malformed rows handled.

### Task 1.7: REST API Endpoints (Day 12–14)

- Endpoints: /api/overview, /api/teams, /api/teams/:team, /api/developers/:id, /api/developers/:id/timeline

- /api/waste, /api/snapshots, /api/export

- JSON responses, pagination, date/team filtering

- Basic auth middleware

Accept: All endpoints return correct data. Pagination and filtering work. Auth enforced. Under 200ms with 10K rows.

### Task 1.8: Waste Detection Engine (Day 14–16)

- Unused seat detector: subscription + zero activity for 14+ days

- Underutilized: usage below 20% of team average

- Duplicate tool detector: overlapping IDE-based or terminal-based tools

- Cost outlier: cost-per-PR >3x team average

- CLI: govproxy waste show / waste summary / waste resolve

Accept: Correctly identifies unused seats, duplicates. No duplicate alerts. Resolved alerts don’t reappear.

### Task 1.9: CLI Summary + Doctor (Day 16–17)

- govproxy status: developers, teams, connectors, subscriptions, waste, data coverage

- govproxy doctor: validates config, database, API tokens, scopes, endpoints

Accept: Status shows accurate summary. Doctor catches missing config, invalid tokens. Works on empty database.

### Task 1.10: Scheduled Sync Pipeline (Day 17–18)

- node-cron scheduler with configurable sync times

- Pipeline: Copilot → Git → (future connectors)

- Sync logging, state tracking, duplicate prevention

- CLI: govproxy sync all / govproxy sync copilot / govproxy sync git

Accept: Scheduled sync runs automatically. Processes only new data. One connector failure doesn’t block others.

# 5. Phase 1 Milestone

After 3 weeks: a working data pipeline pulling from Copilot API and git repos daily, subscription data imported from CSV, waste detection identifying unused and duplicate seats, and a REST API ready for the Phase 2 dashboard.

Test: govproxy doctor (verify setup) → govproxy sync all (pull data) → govproxy status (see summary) → govproxy waste show (see alerts) → curl /api/overview (API works).

# 6. Go / No-Go After Dogfood

### Ship if:

- Data pipeline stable for 4 weeks without manual intervention

- Copilot metrics match vendor dashboard within 5%

- Git analysis produces plausible AI adoption signals

- Waste detection identified at least 2 genuinely wasted seats

- At least 1 manager checked dashboard without being asked

- AI summaries accurate and actionable

- Setup took less than 1 hour

### Don’t ship if:

- Pipeline requires frequent manual fixes

- Copilot metrics diverge significantly from vendor dashboard

- Waste alerts mostly wrong (false positives >20%)

- Dashboard ignored after initial demo

- AI summaries contain inaccurate information

End of Document — GovProxy V1 Build Specification